## Sheet1
Task Name | Category | Sign-off | End Date | Description | Tags | Subtasks
Send proposal to people in JCIT - live meeteing | Propsal |  | 2018-08-28 22:59 |  |  | - Send Lupe copy of digital file.
Send digitial copy to Lupe | Propsal |  | 2018-08-29 15:25
Create example | Propsal |  | 2018-09-12 16:59 |  |  | - Share the attached file to others
Get approval from Steering Committee | Propsal |  | 2018-09-22 06:59
Share with workgroup | Propsal |  | 2018-09-27 21:00
Needs Assessment | Analyze |  | 2018-10-23 06:59
Create Questionarre | Analyze |  | 2018-10-23 06:59 | this is an internal document to determine the scope of the work - this will help determine some of the finer details of the project as well as players involved. Usually part of needs assesment, but done post assesment in this project due to familiarity with audoence history and subject. | - [DELIVERABLE]
Road-map for project [DELIVERABLE] | Analyze |  | 2018-10-23 06:59 | Calendar based road-ap of all milestones and deliverables | - [DELIVERABLE]
Fillout Questionarre | Analyze |  | 2018-10-23 09:00 | We need a questionarre to determine the scope of the project. Similar to the needs assesment, this QA will help guide us throu the process. Pull from the documents you have on the I Drive for
Define Budget hours and tools cost | Propsal |  | 2018-10-26 06:59 | This is a rough estimate of the amount of hours and resources needed for the project. |  | - Hours for project - Cost of tools
Approval of Budget | Propsal |  | 2018-10-26 06:59 | WERC Budget in contract
Map Algorithm to branches | Analyze |  | 2018-10-30 06:59
Roadmap Feedback / Approval | Analyze | C. Gupta | 2018-10-30 06:59 | This approval process is done by the workgroup sub-committee and must be done quickly in order to proceed to the next step(s) | - Call Discussion
Investigate Animation Platforms | Analyze |  | 2018-10-31 06:59
Animation Style Feedback / Approval | Design | C. Gupta | 2018-11-03 07:59 | this shoudl not be a long and tedious discussion, but rather an agreement on one of 3 animation styles. This can be done on the call | - Call Discussion
Animation Examples [DELIVERABLE] | Design |  | 2018-11-06 07:59 | come up with 3-4 animation styles to build out project. i.e. white-board, stick-figures, 2D classic ( could include HB style, infographic style...etc.) for the team to choose from. | - [DELIVERABLE]
Task Analysis - Action Map | Analyze |  | 2018-11-07 07:59 | Internal discussion about what actions will be required to practice to help devlop the flow of game and instruct wireframe.
Choose Animation Platform | Design |  | 2018-11-16 07:59 | Will need approval for animation style to know which program will be the best for selected styles. |  | Assess each - Powtoons - Vyond - Reallusion / CrazyTalk - Animatron - Animaker - Muvizu
Wire Frame [DELIVERABLE] | Design |  | 2018-11-20 07:59 | Wireframe of training w/o any animation or style - the bare bones of the training based on the action map Wireframes must be approved. | - [DELIVERABLE]
Wireframe Approval | Design | A. Booth | 2018-11-27 07:59 | This approval may taek a bit longer, as all elelments of training are mapped out in a wireframe Will gove a week. | - Call Discussion
StyleGuide [DELIVERABLE] | Design |  | 2018-11-27 07:59 |  | - [DELIVERABLE]
Script Re-writes | Design |  | 2018-12-03
Approve Styleguide | Design | C. Gupta | 2018-12-04 07:59 |  | - Call Discussion
Narrative Examples | Design |  | 2018-12-05 07:59 | This contains options for the actual story and the characters, includining how they will be presented in a Just Culture scenario.
Choose Narrative | Design |  | 2018-12-11 07:59 |  | - Call Discussion
Script [DELIVERABLE] | Design |  | 2018-12-11 07:59 |  | - [DELIVERABLE] | - Write Scenerio - Feedback/ Approval of Scenerio - Voice Over - Feedback / Approval Voice Over
Script Feedback / Approval | Design | C. Gupta | 2018-12-18 07:59 |  | - Comment Document
StoryBoard [DELIVERABLE] | Design |  | 2018-12-18 07:59 | Contains the actual characters and narrative with images to indicate the actions and animations that will be presented in the actual product. | - [DELIVERABLE]
Approve Storyboard Feedback / Approval | Design | E. Ramirez | 2019-01-01 07:59 |  | - Comment Document
Build out Articulate Storyline | Develop |  | 2019-01-08 07:59 | This is the framework that will hold the animation and narrative. A simplified version of text and workflow will need to be built from the wireframe.
Storyboard Corrections | Design | E. Ramirez | 2019-01-08 07:59 |  | - Call Discussion
Develop Animation Assets | Develop |  | 2019-01-22 15:51
Add Animation | Develop |  | 2019-01-31 07:59 |  |  | - Crate animation assets - Insert into Articulate - Set timing
Articulate Alpha [DELIVERABLE] | Develop |  | 2019-02-05 07:59 |  | - [DELIVERABLE]
Alpha Review - Feedback / Approval | Develop | Committee | 2019-02-12 07:59 |  | - Call Discussion
Articulate Beta [DELIVERABLE] | Develop |  | 2019-02-19 |  | - [DELIVERABLE]
Version Corrections | Develop |  | 2019-02-25
Beta Review -Feedback / Approval | Develop | Committee | 2019-02-26 07:59 |  | - Call Discussion
Determine the parameters of the pilot | Implement |  | 2019-03-04 07:59
Articulate Final [DELIVERABLE] | Develop |  | 2019-03-12 06:59 |  | - [DELIVERABLE]
Version Corrections | Develop |  | 2019-03-15 06:59
Load to Learning Net | Implement |  | 2019-03-18 06:59
Final Review - Feedback / Approval | Develop | R. HAll | 2019-03-20 06:59
Test Learning Net | Implement |  | 2019-04-11
Move to official LN | Implement |  | 2019-04-19
Pilot Audience | Implement |  | 2019-04-19 06:59 | Determine Best Audience for Pilot
Evaluation Materials | Evaluate |  | 2019-05-01 06:59
Run Pilot | Implement |  | 2019-05-02 06:59
Run Evaluation | Evaluate |  | 2019-05-31 06:59
Survey Pilot | Evaluate |  | 2019-06-03 06:59